Design and Implementation of a Training Program for Pharmacist Response to Code Blue Emergencies in the Hospital Setting

Terminal Master’s Project:  Dale Tucker, May 2006

| Project description and purpose | Using the format of concept mapping, a training program will be developed for the pharmacists at Harper University Hospital to increase their competency in code blue emergency participation. Because many of the staff are new employees and/or new graduates with minimal or no experience in this area, a formal training program is recommended. Concept mapping will be used to direct self-study training in a step-by-step manner allowing the pharmacists to learn and master the information at times convenient to their schedules either when the lecture format is unavailable or to enhance the lecture learning method. |
| --- | --- |
| Rationale | Departmental management supports training for pharmacists to participate in code blue emergencies noting Code blue emergencies do not occur on a regular basis making a review of needed knowledge to participate in them essential Many pharmacists are new to the department and/or new to pharmacy and lack any training or experience in this area In addition, the American Society of Health System Pharmacists (ASHP) residency accreditation survey in October 2005 emphasized the need to include such training for pharmacy residents Concept mapping would be used to organize the knowledge as well as make it accessible and actionable for the pharmacists Knowledge acquisition would be emphasized to allow for the development of skills and education necessary to participate in code blue emergencies using multiple learning techniques Knowledge sharing would be enhanced with concept mapping allowing for a visual view of the relationships between the learning components Knowledge utilization would be enhanced allowing participation in code blue emergencies to become an integrated clinical function of all pharmacists |
| Target audience | All pharmacists and pharmacy residents in the Harper University Hospital pharmacy department |
| Instructional setting | Harper University Hospital pharmacy department conference room and departmental website |
| Instructional goals and objectives | Reinforce pharmacists’ knowledge of medications and procedures used during these emergencies through lecture and self-study Improve pharmacists’ comfort level/familiarization with tasks and responses used during code blue emergencies through examples given in lecture and self-study format Enhance retention of information through the use of a hands-on mock code blue practical examination |
| Deliverables | Lecture/self study module of medications and responses used in code blue emergencies including medication doses, rates of infusion, and various modes of administration Lecture/self-study module to learn the crash cart contents in addition to the medications Lecture/self-study module to learn the pharmacist’s role in assisting at code blue emergencies One-on-one practical assessment guide to determine the pharmacists’ ability to participate in a code blue emergency A written and/or online exam of the three lecture sections A written and/or online evaluation of each of the four sections Videos of lecture portions |
| Supporting materials | Four PowerPoint and/or written training modules as appropriate Videos of lectures Self assessment questions for each section Evaluations of each section Crash cart availability to use during live training session |
| Evaluation | Evaluation forms to be filled out at the completion of each of the three or four sections; sections two and three may be combined when presented |
| Timeline | January 24 | Submit proposal to Ray Amirault, PhD |
|  | February 3 | Update lecture/handout for Krista Piekos-Wahby on medications and responses used in code blue emergencies |
|  | February 10 | Write lecture/handout on contents other than medications in code blue crash cart |
|  | February 17 | Write lecture/handout on pharmacist’s role during a code blue emergency |
|  | March 3 | Write a trainer’s guide to mock code setup for administration to pharmacists |
|  | March 10 | Write evaluations and exams for each of the four sections of the training using surveygold.com |
|  | March 17 | Complete concept maps |
|  | March 20-24 | (1) Implement training using pharmacy residents planning a 3 hour time block (2) video tape lectures (3) use evaluations to improve training plan |
|  | March 31 | Make needed changes, insert video in concept map, and submit for final assessment |
|  | April 5 | Make any needed improvements and submit final project to Ray Amirault, PhD |
|  | April 10 | Title, 3 line description, and equipment needs delivered to Michele Norris |
|  | April 14 | Complete poster |
|  | April 22 | Poster presentation session from 10am until 12noon |
| Sign-off points | February 10 | Two PowerPoint lectures |
|  | March 3 | Third PowerPoint lecture and a mock code manual |
|  | March 17 | Evaluation forms, exams, concept map(s) |
|  | March 31 | Evaluate program implementation, complete videos and insert in concept map |
| Stakeholder commitment | Response to code blue emergencies has been done in the past by the department. It was stopped a number of years ago due to scheduling conflicts. Currently, the department is committed to returning to the model of pharmacist involvement in response to code blue emergencies. It is noted that the ASHP residency accreditation survey in October 2005 also emphasized that the pharmacy residency training needed to include involvement in code blue emergencies. |