## Full Grants Schedule Checklist
Full-Grants Schedule Checklist
Project Title:
RFA Announcement Date: Proposal Delivery Date:
Working Days to Produce Proposal:
Midpoint: Days:
NOTE: The following timeline is dependent upon fully resolving all ALIGNMENT issues
Tasks |  | OSHL/Other Partners/Collaborators | Due Date | Date Actually Delivered
1. Alignment
a) Sole Grant or Parnership/Program (check one)
Sole/Exist. Prog.
Sole/New Prog.
Exist. Ptnr/Exist. Prog.
Exist. Ptnr./New Prog.
New Ptnr/Exist. Prog.
New Ptnr./New Prog.
b) Team Coordinator/Lead
c) Site/(s) to be confirmed
d) Program Design & In/Above Budgt. Percentages
2. Contractor/Writer- Yes/No
3. RFA to Legal & Finance for review
4. Draft Prog. Budgt/Refer to Finance
5. Meeting with Team
6. Draft #1
7. List of Potential Partners by Country or State or Site
8. Comments on Draft #1 (identify each commentator) | name:
name:
name:
name:
name:
9. Signed Letters of Support, if applicable as applicable
10. Draft #2
11. Comments on Draft # 2 (identify each commentator) | name:
name:
name:
name:
12. Final Budget Adjustment
13. Final Narrative and Budget
14. Complete Packaging
15. Deliver Proposal
Note:
Team Coordinator/Lead reviews RFA and prepares summary for team discussion
Team Coordinator/Lead schedule initial meeting with team
Teams determines if a grants writer is to be hired
Legal and Financial sufficiency